## Sheet1
When | To-Do Item | Notes and Resources | Task Assigned to | Task Status
Eight Weeks From Event | Define event objectives and key takeaways | Will this be a social event, centered around a topic discussion or a conference setting with sessions.
Eight Weeks From Event | Create a draft agenda | Need agenda from AL & SoCAl in toolkit
Eight Weeks From Event | Select the event date & time
Seven Weeks From Event | Select a meeting platform | Virtual Meeting Platform Information spreadhseet & also include a link here to information about how they can use our platform (this information is to come)
Seven Weeks From Event | Inform the national office of your upcoming event to place it on CUPA-HR's calendar of events | Submit an Event Promotion Form
Six Weeks From Event | Determine how a corporate sponsor can contribute to the event | Some suggestions are shared in the Chapter Management Community
Six Weeks From Event | Invite corporate sponsor | Connect with CUPA-HR Corporate Members
Six Weeks From Event | Select facilitators | Select presenters and determine who will be speaking during your event.
Five Weeks From Event | Finalize agenda
Five Weeks From Event | Create registration form | Your meeting platform may provide a registration link. If so, make sure you will have access to your registration list once your event ends.
Five Weeks From Event | Set registration deadline | Determine if your meeting platform will accept registrations up to the live event.
Five Weeks From Event | Update chapter website | Your final agenda and registration information should be added to your website.
Four Weeks From Event | Request an email be sent to everyone in your chapter area. | Include meeting agenda, registration information and contact information for questions. Submit an Email Request Form.
Three Weeks From Event | Create an outline or script for speakers and facilitators | This will help the flow of your event and will ensure that everyone speaking knows when to speak and what to say. Be sure to designate time for your sponsors to speak and assign a board member to introduce them. You sponsor may provide a bio or introduction you can share.
Two Weeks From Event | Review registration numbers and determine if reminders/additional outreach is necessary | Submit an Event Promotion Form
One Week From Event | Create evaluation survey to send to attendees after the event
One Week From Event | Conduct a test event in your meeting platform to familiarize yourself with the functionality of the meeting platform.