## To-Do List - Chapter Events
When | To-Do Item | Notes and Resources | Task Assigned to | Task Status
Six Months From Event | Determine the Date of the Chapter Meeting/Conference | Reference the CUPA-HR Calendar of Events to make sure your event doesn't conflict with region or national events.
Six Months From Event | Determine the location of the Meeting/Conference | Review the event planning resources in the toolkit for assistance with hotel contracting and site selection.
Six Months From Event | Establish budget
Six Months From Event | Place the event information on your website
Six Months From Event | Inform the national office of your upcoming event | Submit an Event Promotion Form
Six Months From Event | Form a Planning Committee for program/event planning
Six Months From Event | Begin discussions of potential topics and speakers. Think about current hot topics and reveiew previous survey feedback for topics. | Utilize personal contacts, colleagues, your region board and other sources for determining possible speakers.
Six Months From Event | Determine compensation/reimbursement of travel, etc. for speakers
Six Months From Event | Determine if registration is required of speakers, if so, determine rate
Six Months From Event | Create a Sponsorship Prospectus | Explore the corporate partner sponsorship resources in the toolkit.
Three to Four Months From Event | Determine and finalize topics/speakers
Three to Four Months From Event | Assign task of reaching out to secure speakers that have not been finalized
Three to Four Months From Event | Draft an agenda of the meeting/conference | Sample agendas are located in the toolkit.
Three to Four Months From Event | Determine registration rate and method of registration. | Sample registration forms are located in the toolkit.
Three to Four Months From Event | Add the registration information to your chapter website.
Three to Four Months From Event | Determine if continuing education credits will be submitted for pre-approval | Information on continuing education unit resources located in the toolkit.
Two Months From Event | Invite higher education human resources professionals to your event | Sumbit a Chapter E-mail Request Form
Two Months From Event | Determine feedback/survey form needed for use after event (available at meeting OR via email) | Sample evaluation surveys are located in the toolkit.
Two to Four Weeks Prior to Event | Review registration numbers and determine if reminders/additional outreach is necessary | Submit an Event Promotion Form
Two to Four Weeks Prior to Event | If conducting personal outreach, assign institutional contacts to planning committee OR other chapter leadership team members | Reference the region contact list in CUPA-HR Connect.
Two to Four Weeks Prior to Event | Plan Food and Beverage with catering – be mindful of dietary restrictions and accommodations
Two to Four Weeks Prior to Event | Review budget
Two to Four Weeks Prior to Event | Utilize tax exemption, if applicable, to avoid taxes
One Week Prior To Event | Review registration information
One Week Prior To Event | Create name badges
One Week Prior To Event | Update number of attendees with caterer to finalize food and beverage total
One Week Prior To Event | Send a personal reminder email to registered attendees of the upcoming event
One Week Prior To Event | Finalize sponsorship relationships
One Week Prior To Event | Confirm sponsors' registration, if necessary
One Week Prior To Event | Send sponsors a list of attendees (name, title and institution only)
One Week Prior To Event | Confirm signage needed
One Week Prior To Event | Confirm any speaking arrangements
One Week Prior To Event | Assign tasks to chapter leadership of needed work on the day of event – pictures, info desk, speaker go to for troubleshooting, etc.
After the Event | E-mail evaluation survey to attendees
After the Event | Compile/download the survey results
After the Event | Discuss the evaluation results and de-brief of event – makes notes for future planning.
After the Event | Determine a way of thanking corporate partners again (phone calls/emails)
After the Event | Update the chapter website. (Thank the attendees, post pictures, slides/handouts, etc.)
After the Event | Thank planning committee
After the Event | Financials – ensure timely payment of invoices, ensure all registration money received (if charge), collect any funds from sponsor, etc
After the Event | Treasurer (or other designated chapter leadership position) captures information for financial report